## Sheet1
| Tasks | May | Jun | Jul | Aug | Sep | Oct
1 | Project Initiation
2 | Budget Approval (Dev server if appl; align expiry data; explorer/viewer license)
3 | Convert desktop to server (creator license)
4 | Align creator license expiry date
5 | Procure explorer/viewer license
6 | 14-Day Tableau Virtual Bootcamp
7 | Prepare Dev Server
8 | Prepare Prod Server
9 | Prepare DR server
10 | Traning for Creators
11 | Training for Viewers
12 | UAT and Testing
13 | Mnagement Report
14 | System Release